## V1
Project Development and Completion Tracker
Porject ID: Version 1.2 (Flutter)
Project Start Date: 15-07-2024 Project End Date: 18-11-2024
Porject Descreption: Intelligent Traffic Management System project
| Name of Team member |  |  | Name of Students |  | Role
Project Architech Team Members | Shaaz Mukadam |  | Project Development Student Team Memebers | Shaaz Mukadam |  | Team Lead
| Aadityanarayan Jha |  |  | Aaditya | Vishal | Frond End
| Vishal Sakale |  |  | Aaditya |  | Team Lead
| Pratham Desai |  |  | Pratham | Aaditya | Front/Back End
|  |  |  | Shaaz Mukadam |  | Team Lead
|  |  |  | Pratham | Aaditya | Back End
|  |  |  | Vishal |  | Front End
Epic: | As a city commuter or traffic authority, I should experience seamless traffic flow management and improved safety using AI-powered systems that dynamically manage traffic signals and prioritize emergency vehicles.
Story 1: | As a commuter, I should be able to see real-time traffic updates and congestion levels in my city.
Story 2: | As a traffic authority, I should be able to dynamically control traffic signals based on vehicle density and emergency vehicle prioritization.
Story 3: | As a commuter, I should receive alternate route suggestions to avoid congestion or accidents in my area
Task1: | Design a user registration and login system for commuters and traffic authorities with database configuration.
Task2: | Develop a traffic data collection module that integrates with IoT sensors, cameras, and real-time data sources.
Task3: | Integrate Google Maps API for real-time traffic visualization and congestion heatmaps.
Task4: | Develop a module for dynamic traffic signal control based on vehicle density and emergency route prioritization.
Task5: | Implement predictive analytics to forecast traffic congestion using historical data and machine learning algorithms.
Task6: | Design a commuter interface that displays optimal routes, ETAs, and live traffic conditions.
Acceptance Criteria:
1 | Registration layout supports both commuters and traffic authorities with proper input validations.
2 | Traffic visualization accurately reflects congestion levels using Google Maps API integration.
3 | Traffic signals adjust timings dynamically based on vehicle density and emergency vehicle detection.
4 | The system provides alerts about potential congestion and suggests alternate routes.
5 | User-friendly interface displays live traffic data, congestion zones, and suggested routes.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Design traffic data collection module with database configuration. | Set up a database schema to store collected traffic data. | Complete | Shaaz ,Pratham | 2024-07-03 | 13-07-2024 | 03-07-2024 |  | 100% | Complete | Medium
|  | Configure data collection devices | Complete | Vishal ,Aditya | 2024-07-20 | 30-07-2024 | 2024-07-22 |  | 100% | Complete
| Develop user interface for real-time traffic monitoring | Design a dashboard layout for displaying real-time traffic information. | Complete | Shaaz ,Pratham | 2024-08-03 | 2024-08-12 | 2024-08-04 |  | 100% | Complete | Low
|  | Integrate maps and traffic overlays into the UI. | Complete | Vishal ,Aditya | 2024-08-20 | 2024-08-25 | 2024-08-21 |  | 100% | Complete
| Integrate Google Maps API to visualize traffic conditions and manage routes. | Set up Google Maps API in the project environment. | Complete | Shaaz ,Pratham | 2024-09-03 | 2024-09-12 | 2024-09-04 |  | 100% | Complete | High
|  | Fetch and display live traffic data on the map. | Complete | Vishal ,Aditya | 2024-09-20 | 2024-09-25 | 2024-09-21 |  | 100% | Complete
| Implement dynamic traffic signal control system with AI algorithms. |  | Complete | All | 2024-10-02 | 02-10-2024 | 2024-10-02 |  | 100% | Complete
Sprint 1 | Develop predictive analytics module for traffic congestion detection and prevention | Collect historical traffic data for model training | Complete | Shaaz ,Pratham | 2024-10-11 | 15-10-2024 | 2024-10-11 |  | 100% | Complete
| Design a system to prioritize emergency vehicles using real-time traffic data | Configure traffic signals to detect emergency vehicles | Complete | All | 2024-10-16 | 22-10-2024 | 2024-10-17 |  | 100% | Complete
| Integrate and test all modules for seamless operation of the Intelligent Traffic Management System | Combine traffic data collection, UI, and AI modules. | Complete | All | 2024-10-25 | 02-11-2024 | 2024-10-26 |  | 100%
12
10
10
10
10
15
15
20
20
20
20
10
20
20
15
15
10
20
20
15
15
20
342
65
407

## Version 2
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%

## Student Team
STUDENT INTERN LIST
Sr. No. | Name of Inern | Email Address | Contact | class | Domain (Web, App, Backend)
1 | Prajwal Sah | prajwalsah212@gmail.com | 7776012981 | FY IT DA | ML
2 | Shriya Dilliwale | anitashriya12@gmail.com | 7559361354 | FY IT DA | Flutter, ML | Version 1
3 | Nikhil Chavan | nikhilchavan407@gmail.com | 8369686747 | FY IT - CORE | Flutter | Version 1
4 | Vipul Kumar Singh | vipulkumarbhore@gmail.com | 7764059016 | FY IT - CORE | Flutter | Version 2
5
6
8
9
10
3 | Anjali Bhatt | anjalibhatt601@gmail.com | 830811254 | FY CSE Core 2 | Flutter, ML | Version 1
4 | Shruti Singasane | singasane.shruti2001@gmail.com | 8652233102 | FY CSE Core 2 | Flutter, ML | Version 1
5 | Rushil Jain | rushiljain2001@gmail.com | 9371775841 | FY CSE IS 1 | Flutter, ML | Version 1
7 | Sumeet Sapkal | sumeetspkl@gmail.com | 9112156784 | FY CSE | Flutter, MySQL | Version 2
8 | Sunny Yadav | sunnyyadavtheone@gmail.com | 7878964402 | FY CSE | Flutter, MySQL | Version 2
9 | Siddhant Oswal | oswalsiddhant2001@gmail.com | 8329979013 | FY CSE | Flutter | Version 2
10 | Simon Singh | simonsinghdomain@gmail.com | 7470659108 | FY CSE | Flutter | Version 2
11 | Varun Kapse | varunkapse07@gmail.com | 8830624385 | FY IT - PASSED | ML | Version 2
13 | Rutvi Nair | rutvinar305098@gmail.com | 8141393918 | TY CSE IS 1 | Flutter | Version 2